## Samenvatting
Lostock Fabric — Meetstaten Samenvatting
Productie- en inmeetgegevens isolatiematrassen (SIB Isolatie / Hotrema)
Opdrachtgever: | Hotrema |  | PROJECT TOTAAL (ST.) |  |  | AANTAL MATRASSEN (ST.) | AANTAL PETTEN | DATABASE DETAILS (ST.)
Project: | Lostock Fabric
Uitvoering: | Sil-HT700-wol
Inmeters: | JV & RdW (Ron de Wit)
Inmeetperiode: | 9 juni 2026 t/m 12 juni 2026
Rapportagedatum: | 23 juni 2026
Dag | Datum | Project Totaal (st.) | Database Details (st.) | m2 Details (m2) | Gewicht Details (kg) | Waarde Details (€)
1e dag | 09-06-2026 | 519
2e dag | 10-06-2026 | 339
3e dag | 11-06-2026 | 520
4e dag | 12-06-2026 | 185
Totaal

## Meetstaten Details
2026-06-12 | [5 empty] | Location | 170
[9 empty] | prijs |  | PRIJS
nummer | Aantal | nummer | omvang | hoogte | Gesp/haken |  |  | m2 |  | labels |  | kg | Verdieping | Datum | Inmeter | Bovendoek | Onderdoek
Lostock Fabric | 2 | 278 | 1.1 | 0.55 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 2 | 279 | 1.1 | 0.45 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 2 | 280 | 1.1 | 0.68 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 281 | 1.8 | 0.36 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | log | N/A
Lostock Fabric | 1 | 281 | 0.57 | 0.57 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | log | N/A
Lostock Fabric | 1 | 282 | 0.36 | 0.3 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 283 | 0.36 | 0.26 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 284 | 0.36 | 0.46 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 2 | 285 | 0.66 | 0.28 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 286 | 1.36 | 0.65 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 287 | 1.36 | 0.66 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 288 | 0.4 | 0.48 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 2 | 289 | 0.31 | 0.74 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 290 | 0.43 | 0.28 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 291 | 2.28 | 0.47 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 291 | 0.73 | 0.73 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 292 | 0.36 | 0.45 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 3 | 293 | 0.66 | 0.33 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 294 | 1.5 | 0.3 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 294 | 0.48 | 0.48 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 295 | 0.36 | 0.37 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 296 | 1.5 | 0.9 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 297 | 1.58 | 0.38 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 298 | 2.28 | 0.46 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 298 | 0.73 | 0.73 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 299 | 1.25 | 0.28 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | /56 | /56
Lostock Fabric | 2 | 300 | 0.36 | 0.32 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 301 | 2.21 | 0.43 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 301 | 0.7 | 0.7 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 302 | 1.07 | 0.26 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 302 | 0.34 | 0.34 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 303 | 2.22 | 0.88 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | /0 | N/A
Lostock Fabric | 2 | 303 | 0.71 | 0.71 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | /0 | N/A
Lostock Fabric | 2 | 304 | 2.22 | 0.38 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | 4g | N/A
Lostock Fabric | 1 | 305 | 1.06 | 0.5 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 306 | 1.07 | 0.28 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 306 | 0.34 | 0.34 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 308 | 1.07 | 0.25 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 309 | 1.82 | 0.29 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | /56 | /56
Lostock Fabric | 1 | 309 | 0.58 | 0.58 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | /56 | /56
Lostock Fabric | 1 | 310 | 0.36 | 0.72 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 311 | 0.66 | 0.38 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 312 | 0.36 | 0.15 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 313 | 0.36 | 0.46 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 314 | 0.66 | 0.58 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 2 | 315 | 1.8 | 0.5 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | log | N/A
Lostock Fabric | 2 | 315 | 0.57 | 0.57 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | log | N/A
Lostock Fabric | 2 | 316 | 0.36 | 0.46 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 2 | 317 | 0.36 | 0.16 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 2 | 318 | 0.66 | 0.18 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | log | N/A
Lostock Fabric | 2 | 318 | 0.21 | 0.21 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | log | N/A
Lostock Fabric | 1 | 320 | 1.75 | 0.4 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 320 | 0.56 | 0.56 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 322 | 1.81 | 0.54 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | /56 | /56
Lostock Fabric | 1 | 322 | 0.58 | 0.58 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | /56 | /56
Lostock Fabric | 2 | 323 | 0.36 | 0.26 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 2 | 324 | 0.36 | 0.32 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 325 | 0.36 | 0.46 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 326 | 0.66 | 0.25 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 327 | 1.78 | 0.51 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 328 | 1.25 | 1.12 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 329 | 1.25 | 0.32 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 329 | 0.4 | 0.4 | G/H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 330 | 2.13 | 0.96 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 331 | 1.07 | 0.3 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 331 | 0.34 | 0.34 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 332 | 0.66 | 0.34 | H | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Peter | 5 Zs | N/A
Lostock Fabric | 1 | 333 | 0.75 | 0.32 | G | Turbine Hall |  |  | 190 |  |  |  | Turbine Hall | 12-06-2026 | Ron | N/A | N/A
Lostock Fabric | 12 | 1 | 0.66 | 0.29 | G |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 24 | 2 | 1.03 | 0.28 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /56 | /56
Lostock Fabric | 24 | 2 | 0.33 | 0.33 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /56 | /56
Lostock Fabric | 36 | 3 | 0.72 | 0.14 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | be | N/A
Lostock Fabric | 36 | 3 | 0.23 | 0.23 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | be | N/A
Lostock Fabric | 12 | 4 | 0.75 | 0.32 | G |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 36 | 5 | 0.7 | 0.56 | G |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /56 | /56
Lostock Fabric | 12 | 6 | 1.03 | 0.32 | G |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /56 | /56
Lostock Fabric | 12 | 7 | 2.57 | 0.36 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 12 | 7 | 0.82 | 0.82 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 12 | 8 | 2.91 | 0.58 | G |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 16 | 9 | 0.75 | 0.28 | G |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 16 | 10 | 1.05 | 0.28 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 16 | 10 | 0.33 | 0.33 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 16 | 11 | 1.08 | 0.28 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 16 | 11 | 0.34 | 0.34 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 16 | 12 | 2.83 | 0.56 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 16 | 12 | 0.9 | 0.9 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 24 | 13 | 2.49 | 0.52 | G |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /56 | /56
Lostock Fabric | 8 | 14 | 2.83 | 0.52 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 8 | 14 | 0.9 | 0.9 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 8 | 15 | 0.77 | 0.89 | H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | log | N/A
Lostock Fabric | 4 | 16 | 0.33 | 0.33 | H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /56 | /56
Lostock Fabric | 8 | 17 | 0.35 | 0.4 | H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 3 | 18 | 1.08 | 0.25 | G/H |  |  |  | 190 |  |  |  | Ground Floor | 09-06-2026 | Peter | YS | N/A
Lostock Fabric | 3 | 18 | 0.34 | 0.34 | G/H |  |  |  | 190 |  |  |  | Ground Floor | 09-06-2026 | Peter | YS | N/A
Lostock Fabric | 3 | 19 | 0.66 | 0.14 | H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /0 | N/A
Lostock Fabric | 3 | 20 | 1.08 | 0.25 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /0 | N/A
Lostock Fabric | 3 | 20 | 0.34 | 0.34 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /0 | N/A
Lostock Fabric | 1 | 21 | 0.74 | 0.34 | G |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | log | N/A
Lostock Fabric | 8 | 22 | 0.88 | 0.2 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 8 | 22 | 0.28 | 0.28 | G/H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 5 | 23 | 0.75 | 0.3 | G |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /56 | /56
Lostock Fabric | 4 | 24 | 0.55 | 0.6 | H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | log | N/A
Lostock Fabric | 1 | 25 | 0.8 | 0.36 | G |  |  |  | 190 |  |  |  | 2nd Floor | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 26 | 0.59 | 0.25 | G |  |  |  | 190 |  |  |  | Turbine Hall | 09-06-2026 | Ron | N/A | N/A
Lostock Fabric | 1 | 27 | 0.61 | 0.13 | G |  |  |  | 190 |  |  |  | Ground Floor | 09-06-2026 | Peter | 4g | N/A
Lostock Fabric | 1 | 28 | 2.66 | 1 | G |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 29 | 0.28 | 0.23 | G |  |  |  | 190 |  |  |  | Turbine Hall | 09-06-2026 | Ron | N/A | N/A
Lostock Fabric | 2 | 30 | 0.72 | 0.79 | H |  |  |  | 190 |  |  |  | Turbine Hall | 09-06-2026 | Ron | /2 | N/A
Lostock Fabric | 2 | 30 | 0.23 | 0.23 | G/H |  |  |  | 190 |  |  |  | Turbine Hall | 09-06-2026 | Ron | /2 | N/A
Lostock Fabric | 1 | 31 | 0.47 | 0.35 | NO G&H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | /56 | /56
Lostock Fabric | 1 | 32 | 0.4 | 0.4 | NO G&H |  |  |  | 190 |  |  |  | 2 1/2 Floor | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 33 | 0.45 | 0.41 | NO G&H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 34 | 0.41 | 0.41 | NO G&H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 35 | 0.41 | 0.41 | NO G&H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | log | N/A
Lostock Fabric | 1 | 36 | 0.4 | 0.4 | NO G&H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 37 | 0.45 | 0.41 | NO G&H |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 1 | 38 | 0.38 | 0.4 | NO G&H |  |  |  | 190 |  |  |  | Ground Floor | 09-06-2026 | Peter | 4g | N/A
Lostock Fabric | 16 | 39 | 0.83 | 0.21 |  |  |  |  | 190 |  |  |  | Ground Floor | 09-06-2026 | Peter | 5 Zs | N/A
Lostock Fabric | 16 | 39 | 0.26 | 0.26 |  |  |  |  | 190 |  |  |  | Ground Floor | 09-06-2026 | Peter | 5 Zs | N/A
Lostock Fabric | 4 | 40 | 0.9 | 0.9 |  |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 41 | 1.67 | 0.89 |  |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 41 | 0.53 | 0.53 |  |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 8 | 42 | 1.04 | 0.37 |  |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 43 | 1.67 | 0.97 |  |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 43 | 0.53 | 0.53 |  |  |  |  | 190 |  |  |  | Dak | 09-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 44 | 0.63 | 1.1 |  |  |  |  | 190 |  |  |  | 2nd Floor | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 44 | 0.2 | 0.2 |  |  |  |  | 190 |  |  |  | 2nd Floor | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 8 | 45 | 0.36 | 0.16 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 46 | 0.53 | 1.32 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | /0 | N/A
Lostock Fabric | 8 | 47 | 0.83 | 0.36 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 8 | 48 | 0.55 | 0.29 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 8 | 49 | 0.78 | 0.33 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 8 | 49 | 0.25 | 0.25 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 50 | 1.42 | 0.52 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 50 | 0.45 | 0.45 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 51 | 1.76 | 0.81 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 51 | 0.56 | 0.56 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 52 | 1.3 | 0.41 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 53 | 1.71 | 0.71 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 54 | 1.92 | 0.95 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 55 | 1.38 | 0.9 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 56 | 1.17 | 0.17 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 56 | 0.37 | 0.37 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 57 | 0.42 | 0.37 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 57 | 0.13 | 0.13 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 58 | 0.32 | 0.15 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 59 | 0.32 | 0.37 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 60 | 0.57 | 0.22 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 61 | 0.65 | 0.47 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | be | N/A
Lostock Fabric | 2 | 61 | 0.2 | 0.2 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | be | N/A
Lostock Fabric | 4 | 62 | 0.15 | 0.09 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 63 | 0.74 | 0.54 |  |  |  |  | 190 |  |  |  | 2nd Floor | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 63 | 0.24 | 0.24 |  |  |  |  | 190 |  |  |  | 2nd Floor | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 64 | 0.82 | 0.51 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | /56 | /56
Lostock Fabric | 4 | 64 | 0.26 | 0.26 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | /56 | /56
Lostock Fabric | 4 | 65 | 1.05 | 0.6 |  |  |  |  | 190 |  |  |  | 2nd Floor | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 66 | 0.67 | 0.51 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | log | N/A
Lostock Fabric | 4 | 66 | 0.21 | 0.21 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | log | N/A
Lostock Fabric | 4 | 67 | 0.67 | 0.62 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | log | N/A
Lostock Fabric | 4 | 67 | 0.21 | 0.21 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | log | N/A
Lostock Fabric | 2 | 68 | 1.13 | 0.35 |  |  |  |  | 190 |  |  |  | 2 1/2 Floor | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 69 | 1.76 | 1.02 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 69 | 0.56 | 0.56 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 70 | 1.92 | 0.72 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 4 | 73 | 0.17 | 0.61 |  |  |  |  | 190 |  |  |  | Dak | 10-06-2026 | Peter | N/A | N/A
Lostock Fabric | 2 | 74 | 0.73 | 0.26 |  |  |  |  | 190 |  |  |  | Turbine Hall | 10-06-2026 | Ron | /2 | N/A
Lostock Fabric | 2 | 74 | 0.23 | 0.23 |  |  |  |  | 190 |  |  |  | Turbine Hall | 10-06-2026 | Ron | /2 | N/A
Lostock Fabric | 4 | 75 | 0.41 | 0.22 |  |  |  |  | 190 |  |  |  | Turbine Hall | 10-06-2026 | Ron | N/A | N/A
Totaal

## Meetstaten Pagina's
Pagina | Datum | Dag | Sectie | Matrassen (st.) | Petten (st.) | Totaal Items | Foto Pagina's | Opmerkingen
2 | 09-06-2026 | 1e dag | Sectie 1 | 156 | 72 |  | 5-19 | Geverifieerd
3 | 09-06-2026 | 1e dag | Sectie 1 | 108 | 56 |  | 5-19 | Geverifieerd
4 | 09-06-2026 | 1e dag | Sectie 1 | 43 | 6 |  | 5-19 | Geverifieerd; Box 22 marked NV is meegeteld
20 | 09-06-2026 | 1e dag | Sectie 2 | 5 | 5 |  | 23-35 | Geverifieerd
21 | 09-06-2026 | 1e dag | Sectie 2 | 8 | 0 |  | 23-35 | Geverifieerd; Geen haken
22 | 09-06-2026 | 1e dag | Sectie 2 | 36 | 24 |  | 23-35 | Geverifieerd
36 | 10-06-2026 | 2e dag | Sectie 3 | 44 | 16 |  | 38-40 | Geverifieerd; Box 50 marked NV is meegeteld
37 | 10-06-2026 | 2e dag | Sectie 3 | 18 | 4 |  | 38-40 | Geverifieerd
41 | 10-06-2026 | 2e dag | Sectie 4 | 28 | 18 |  | 42 | Geverifieerd
43 | 10-06-2026 | 2e dag | Sectie 5 | 26 | 4 |  | 44-46 | Geverifieerd; Incl. doorgestreepte matrassen
47 | 10-06-2026 | 2e dag | Sectie 6 | 20 | 4 |  | 48 | Geverifieerd
49 | 10-06-2026 | 2e dag | Sectie 7 | 12 | 1 |  | 50-51 | Geverifieerd
52 | 10-06-2026 | 2e dag | Sectie 8 | 21 | 0 |  | 60-84 | Geverifieerd
53 | 10-06-2026 | 2e dag | Sectie 8 | 21 | 0 |  | 60-84 | Geverifieerd
54 | 10-06-2026 | 2e dag | Sectie 8 | 11 | 0 |  | 60-84 | Geverifieerd
55 | 10-06-2026 | 2e dag | Sectie 8 | 15 | 0 |  | 60-84 | Geverifieerd
56 | 10-06-2026 | 2e dag | Sectie 8 | 16 | 2 |  | 60-84 | Geverifieerd
57 | 10-06-2026 | 2e dag | Sectie 8 | 20 | 0 |  | 60-84 | Geverifieerd; Datum op blad heeft typefout 10-5
58 | 10-06-2026 | 2e dag | Sectie 8 | 27 | 0 |  | 60-84 | Geverifieerd
59 | 10-06-2026 | 2e dag | Sectie 8 | 11 | 0 |  | 60-84 | Geverifieerd
85 | 11-06-2026 | 3e dag | Sectie 9 | 14 | 0 |  | 90-95 | Geverifieerd
86 | 11-06-2026 | 3e dag | Sectie 9 | 33 | 0 |  | 90-95 | Geverifieerd
87 | 11-06-2026 | 3e dag | Sectie 9 | 81 | 1 |  | 90-95 | Geverifieerd; Box 171 doorgestreept en meegeteld
88 | 11-06-2026 | 3e dag | Sectie 9 | 9 | 0 |  | 90-95 | Geverifieerd
89 | 11-06-2026 | 3e dag | Sectie 9 | 7 | 0 |  | 90-95 | Geverifieerd
96 | 11-06-2026 | 3e dag | Sectie 10 | 48 | 0 |  | 97-98 | Geverifieerd
99 | 11-06-2026 | 3e dag | Sectie 11 | 24 | 9 |  | 104-106 | Geverifieerd; Box 203 doorgestreept en meegeteld
100 | 11-06-2026 | 3e dag | Sectie 11 | 51 | 0 |  | 104-106 | Geverifieerd
101 | 11-06-2026 | 3e dag | Sectie 11 | 42 | 0 |  | 104-106 | Geverifieerd
102 | 11-06-2026 | 3e dag | Sectie 11 | 48 | 0 |  | 104-106 | Geverifieerd
103 | 11-06-2026 | 3e dag | Sectie 11 | 45 | 0 |  | 104-106 | Geverifieerd
107 | 12-06-2026 | 4e dag | Sectie 12 | 3 | 0 |  | 110-111 | Geverifieerd
108 | 12-06-2026 | 4e dag | Sectie 12 | 16 | 0 |  | 110-111 | Geverifieerd
109 | 12-06-2026 | 4e dag | Sectie 12 | 12 | 0 |  | 110-111 | Geverifieerd
112 | 12-06-2026 | 4e dag | Sectie 13 | 11 | 2 |  | 117-131 | Geverifieerd
113 | 12-06-2026 | 4e dag | Sectie 13 | 16 | 0 |  | 117-131 | Geverifieerd
114 | 12-06-2026 | 4e dag | Sectie 13 | 17 | 0 |  | 117-131 | Geverifieerd
115 | 12-06-2026 | 4e dag | Sectie 13 | 1 | 0 |  | 117-131 | Geverifieerd; Slechts 1 matras (met slash /)
116 | 12-06-2026 | 4e dag | Sectie 13 | 2 | 0 |  | 117-131 | Geverifieerd
132 | 12-06-2026 | 4e dag | Sectie 14 | 7 | 1 |  | 133-143 | Geverifieerd; Exclusief lijstbestelling
144 | 12-06-2026 | 4e dag | Sectie 15 | 35 | 17 |  | 148-155 | Geverifieerd
145 | 12-06-2026 | 4e dag | Sectie 15 | 11 | 2 |  | 148-155 | Geverifieerd
146 | 12-06-2026 | 4e dag | Sectie 15 | 10 | 0 |  | 148-155 | Geverifieerd
147 | 12-06-2026 | 4e dag | Sectie 15 | 3 | 0 |  | 148-155 | Geverifieerd
Extra / Lijstbestellingen (Repetities) |  |  |  | 127 | 0 |  |  | Standard repetities zonder tekening (108 dag 3, 19 dag 4)
Totaal